## Tabellenblatt1
| Epic | Description | Priority | Effort | Status | Details
1 | Admin | As an admin I want to verify added Games/Activities and Events | !! | 3 | Done
2 | Admin | As an admin I want to edit/delete added Games/Activities and Events | !! | 6 | Done
3 | Design | As a user i want to have a well designed page on desktop | !! | 13 | In Progress
4 | Design | As a user i want to have a well designed and responsive page on mobile | !! | 21 | Done
5 | Event | As a user I want to get a list of events | !! | 8 | Done
6 | Event | As a user I want to add new events | ! | 3 | Done
7 | Event | As a user I want to filter events | !! | 5 | Done
8 | Event | As a user I want to change events that i have added | ! | 3 | Done
9 | Event | As a user i want to get cab companies | !!! | 3 | Done
10 | Event | As a user i want to have public transport information | !! | 5 | Planned
11 | Event | As a user i want to have recommended events based on previous clicked ones | !! | 13 | Done
12 | Event | As a user i want to favorize events that i like and list them | ! | 5 | Done
13 | Event | As a user i want the events to be seperated by categories | !! | 8 | Done | Algorithm can be optimized by time
14 | Facebook | As a user i want to log in with facebook | !!! | 5 | Done
15 | Game | As a user I want to get a list of games | !! | 2 | Done
16 | Game | As a user I want to rate games with stars | !! | 2 | Done
17 | Game | As a user I want to add games | ! | 3 | Done
18 | Game | As a user I want to filter games | !! | 5 | Done
19 | Game | As a user I want to change games that i have added | ! | 3 | Done
20 | Game | As a user i want to favorize games that i like and list them | ! | 3 | Done
21 | Game | As a user i want the games to be seperated by categories | !! | 2 | Done
22 | LandingPage | As a user i want to see statistics on the Landingpage | !! | 3 | Done
23 | LandingPage | As a user i want to choose between three spare-time activity categories | ! | 3 | Done
24 | LandingPage | As a user i want to see an popup with privacy policy etc | ! | 3 | Done
25 | Offers | As a user I want to get a list of leisure time activities | !! | 8 | Done
26 | Offers | As a user i want the offers to be seperated by categories | !! | 5 | Done
27 | Testing | as a User i want to have a 24/7 stable service available | !!! | 13 | Done
28 | General | As a User i want to have Ennui in my native tongue | ! | 8 | In Progress