## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
29 | 10 | 200 | 0.05
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2017-05-02 | 30 |  | 0 | 26 | 19 | 0 | 7 | 200 | 19 | 0.030973
2017-05-16 | 30 |  | 2 | 8 | 19 | 7 | 9 | 226 | 17 | 0.038462
2017-05-30 | 30 |  | 1 | 5 | 17 | 9 | 10 | 234 | 16 | 0.041841
2017-06-13 | 30 |  | 2 | 13 | 16 | 10 | 12 | 239 | 14 | 0.047619
2017-06-27 | 30 |  |  |  | 14 | 12 | 12 | 252 | 14 | 0.047619
2017-07-11 | 30 |  |  |  | 14 | 12 | 12 | 252 | 14 | 0.047619
2017-07-25 | 30 |  |  |  | 14 | 12 | 12 | 252 | 14 | 0.047619
2017-08-08 | 30 |  |  |  | 14 | 12 | 12 | 252 | 14 | 0.047619
2017-08-22 | 30 |  |  |  | 14 | 12 | 12 | 252 | 14 | 0.047619
2017-09-05 | 30 |  |  |  | 14 | 12 | 12 | 252 | 14 | 0.047619
2017-09-19 | 30 |  | 0 | 20 | 14 | 12 | 12 | 252 | 14 | 0.044118
2017-10-03 | 30 |  | 1 | 15 | 14 | 12 | 13 | 272 | 13 | 0.045296
2017-10-17 | 30 |  | 3 | 27 | 13 | 13 | 16 | 287 | 10 | 0.050955
2017-10-31 | 30 |  | 2 | 21 | 10 | 16 | 18 | 314 | 8 | 0.053731
2017-11-14 | 30 |  | 2 | 32 | 8 | 18 | 20 | 335 | 6 | 0.054496
2017-11-28 | 30 |  | 1 | 20 | 6 | 20 | 21 | 367 | 5 | 0.054264
2017-12-12 | 30 |  | 1 | 21 | 5 | 21 | 22 | 387 | 4 | 0.053922
2017-12-26 | 30 |  | 0 | 22 | 4 | 22 | 22 | 408 | 4 | 0.051163
2018-01-09 | 30 |  | 1 | 22 | 4 | 22 | 23 | 430 | 3 | 0.050885
2018-01-23 | 30 |  |  |  | 3 | 23 | 23 | 452 | 1.4735 | 0.050885
2018-02-06 | 30 |  |  |  | 1.4735 | 23 | 23 | 452 | 0 | 0.050885
2018-02-20 | 30 |  |  |  | 0 | 23 | 23 | 452 | 0 | 0.050885
2018-03-06 | 30 |  |  |  | 0 | 23 | 23 | 452 | 0 | 0.050885
2018-03-20 | 30 |  |  |  | 0 | 23 | 23 | 452 | 0 | 0.050885
| 720 |  | 1.2308 | 19.3846
Formulas:
Open Story Points = [Open Story Points, row above]+14
Note on A6: Koksi: 2-Wochensprint Falls der Sprintintervall anders ist, bitte die Formel ändern
Note on C6: Koksi: Falls neue AddOns eingebaut werden (oder ähnliches) dann werden hier die inzukommenten SP ergänzt
Note on D6: Koksi: Wie viele SP am Ende des jeweiligen Sprints geschafft wurden
Note on E6: Koksi: Anzahl der gearbeitetn Stunden in dem jeweiligen Sprints