## Tabelle1
Task | Initial Estimation | Current Estimation | Effort | Remain | Responsible | Priority | Comments | Done
Login Register System (Frontend) | 2h | 2h | 2h | 0h | Markus Geilehner | !! | Add the Login Register Sytem (Frontend) | ✔
Login Register Design | 6h | 6h | 3h | 3h | Simon Gutenbrunner | ! | Design the Login Register System (Frontend)
Login Register System (Backend) | 4h | 4h | 4h | 0h | Markus Geilehner | !! | Implement Login Register System Backend | ✔
Event System connected to database (Backend) | 5h | 5h | 4h | 1h | Markus Geilehner | !! | Missing Endpoint "Add-Event"
Event System Endpoint /nearby | 2h | 2h | 2h | 0h | Markus Geilehner | ! | Endpoint to get nearby events with and without filter | ✔
Event System Backend (Add event with no location) | 2h | 2h | 0h | 2h | Martin Singer | ! | When no location is entered event "disappears"